Call for Expression of Interest

**ASEAN Rabies Elimination Strategy**

**Annex 1
(to be returned as Financial offer)**

|  |  |  |
| --- | --- | --- |
| Deliverables | Days of work (prov.) | **Cost** *(Must include consultancy fees and any additional fees)* |
| Development of a project workplan including reporting timelines to respect deadlines for submission of quality deliverables and the methodology to manage different steps of the review. | 3 | EUR… |
| Kick-off/inception meeting (virtual) | 0.5 | EUR… |
| Desktop review on the implementation of ARES, rabies situation and control programmes of ASEAN Member States | 8 | EUR… |
| Develop revised outline for ARES  | 4 | EUR… |
| Facilitate a workshop with ASEAN members, in particular ASWGL and ASEAN Health Cluster 2 and Contact Points on Rabies Elimination, to revise ARES | 3 | EUR… |
| Develop Theory of Change for ARES | 2 | EUR… |
| Develop a first draft based on the agreed outlines | 6 | EUR… |
| Consult the members and the resource groups/experts – integrate feedback received into the draft report. Circulate in the draft revised ARES to the ASWGL meeting and ASEAN Health Cluster 2 for comments and further revisions and integrate feedback | 6 | EUR… |
| Finalise the document (Submit final strategy) | 2 | EUR… |
| Desktop review on the implementation of ARES, rabies situation and control programmes of ASEAN Member States | 8 | EUR… |
| **Total amount for the entire mission****(*must include consultancy fees and any additional fees*)** | 34.5 days | EUR… |

**The estimated budget for this call for expression of interest is EUR 30 000. Bidders are invited to propose the financial offer they deem most economically appropriate.**

**Accordingly, any financial bid exceeding the estimated budget will be rejected.**

Entity name :

Address :

Name & Title of duly authorised representative:

Date :

Signature :