Call for Expression of Interest

**Development of country level Risk-based ASF Control Strategy**

**Annex 1
(to be returned as Financial offer)**

**Currency[[1]](#footnote-2) : …………………………………………………………………**

1. **Firm tranche**

|  |  |  |
| --- | --- | --- |
| Activity/ Steps | Estimated workload (TBC) (in days) | Cost(must include consultancy fees and any additional fees) |
| Inception and coordination |
| Development of a project workplan including reporting timelines to respect deadlines for submission of quality deliverables and the methodology to manage different steps of the review. | 2 | **…** |
| Kick-off/inception meeting (virtual) | 0.5 | **…** |
| *Conduct study to understand ASF situation in the selected countries*  |
| Desktop review of ASF literatures, reports and other documents  | 3 | **…** |
| Conduct study to understand the ASF situation in the selected country (including consultations with various stakeholders of the Candidate country) | 5 | **…** |
| Develop draft ASF Situation Report  | 2 | **…** |
| Finalize the ASF Situation Report  | 1 | **…** |
| *Develop Risk-based ASF Risk Control Strategy for the Candidate Country*  |
| Develop the outlines of the Risk-based Control Strategy | 2 | **…** |
| Consult with the resource groups/experts and finalise the outlines  | 2 | **…** |
| Conduct country consultations with various stakeholders to get further information of ASF control at country level  | 2 | **…** |
| Develop a first draft based on the agreed outlines (Submit the draft strategy) and present to the Resource Groups  | 5 | **…** |
| Consult the members and the resource groups/experts – integrate feedback received into the draft report  | 2 | **…** |
| Finalise the document (Submit final strategy) | 1 | **…** |
| *Train ASEAN Member States to develop Risk-based ASF Control Strategy*  |
| Develop training materials  | 3 | **…** |
| Train ASEAN Member states to develop risk based ASF Control Strategy | 2 | **…** |
| **TOTAL** (must include consultancy fees and any additional fees) | 32.5 days | **…** |

1. **Conditional tranche**

|  |  |  |
| --- | --- | --- |
| **Deliverables** | **Unit day(s)**  | **Cost**  |
| Support for one additional country | **…***Bidders should indicate the number of days necessary to perform the service* | **…***covering the professional fee of the consultant* |

 Nota bene:

For any currency other than the EURO, the exchange rate used will be that of the day of the submission of the offers (03/08/2022).

WOAH is using the main daily euro foreign exchange rates (reference rates provided by the ECB) accessible in the website of the Banque de France ([Main daily euro foreign exchange rates (reference rates provided by the ECB) | Banque de France (banque-france.fr)](https://www.banque-france.fr/en/statistics/rates/exchange-rates/main-daily-euro-foreign-exchange-rates-reference-rates-provided-ecb)

Entity name :

Address :

Name & Title of duly authorised representative:

Date :

Signature :

1. [↑](#footnote-ref-2)