Call for Expression of Interest

SEA’s National Rabies Plans

**Annex 1  
(to be returned as Financial offer)**

**Currency: EUR**

|  |  |  |
| --- | --- | --- |
| **Deliverables** | **Estimated workload (TBC)**  **(in days)** | **Cost**  **(*must include consultancy fees and any additional fees*)** |
| Development of a project workplan including reporting timelines to respect deadlines for submission of quality deliverables and the methodology to manage different steps of the review. | 3 | **EUR…………** |
| Kick-off/inception meeting (virtual) | 0.5 | **EUR…………** |
| Study rabies situation, facilitate evaluation of National Rabies Control Strategy and determine future needs | 4 | **EUR…………** |
| Develop methodology of national strategy development/revision and the draft Outline of the National Rabies Strategy | 2 | **EUR…………** |
| Facilitate a workshop with the resource groups/experts and other stakeholders to present the draft outline and get inputs for strategy development | 3 | **EUR…………** |
| Develop the first draft of the national strategy based on agreed outline | 6 | **EUR…………** |
| Consult the national core groups/experts – integrate feedback received into the draft report | 3 | **EUR…………** |
| Submit final National Rabies Control Strategy | 2 | **EUR…………** |
| **Total amount for the entire mission**  **(*must include consultancy fees and any additional fees*)** | 23.5 days | **EUR…………** |

Entity name :

Address :

Name & Title of duly authorised representative:

Date :

Signature :